## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Multi-Agent Pipeline System Architecture & Data Flow Design | MUST HAVE | None | Vamshi Krishna | 3- Completed
S1 | S1 | US-002 | MySQL ai_project_mentor Database Schema & Users Table | MUST HAVE | None | Harshitha H S | 3- Completed
S1 | S1 | US-003 | Student Registration & Profile Onboarding Interface | MUST HAVE | US-002 | Muthumenen M | 3- Completed
S1 | S1 | US-004 | Competency Skill Assessment Matrix & Scoring Engine | MUST HAVE | US-003 | Lohith Raj | 3- Completed
S1 | S1 | US-005 | Project Idea Submission Form & Academic Template Cards | MUST HAVE | US-001 | Harsh | 3- Completed
S2 | S2 | US-006 | Feasibility Analysis Agent Engine (88% Viability Score) | MUST HAVE | US-001 | Harshitha H S | 3- Completed
S2 | S2 | US-007 | Scope Definition Agent & Tech Stack Recommendation Agent | MUST HAVE | US-006 | Harshitha H S | 3- Completed
S2 | S2 | US-008 | Node.js Express REST API Endpoints (/api/projects/agent/unified) | MUST HAVE | US-002 | Vamshi Krishna | 3- Completed
S2 | S2 | US-009 | Multi-Agent Control Hub UI & Execution Trigger Cards | MUST HAVE | US-005 | Muthumenen M | 3- Completed
S2 | S2 | US-010 | Real-Time Execution Log Stream Terminal Window | SHOULD HAVE | US-009 | Lohith Raj | 3- Completed
S2 | S2 | US-011 | Active Project Summary Header & Local Payload Storage | MUST HAVE | US-009 | Harsh | 3- Completed
S3 | S3 | US-012 | Dynamic Weekly Check-in Engine & Milestone Badge Shifter | MUST HAVE | US-006 | Harshitha H S | 3- Completed
S3 | S3 | US-013 | Backend Chat API Endpoints & Project Context Storage | MUST HAVE | US-008 | Vamshi Krishna | 3- Completed
S3 | S3 | US-014 | Nova AI Mentor Chat UI & Quick Action Prompt Chips | MUST HAVE | US-013 | Muthumenen M | 3- Completed
S3 | S3 | US-015 | Risk Assessment Agent & Plan-B Fallback Mitigation Generator | MUST HAVE | US-006 | Lohith Raj | 3- Completed
S3 | S3 | US-016 | On-Demand Academic Document Exporter (Synopsis & PDF Generator) | MUST HAVE | US-011 | Harsh | 3- Completed
S4 | S4 | US-017 | End-to-End System Integration & Final Presentation Deck | MUST HAVE | US-012 | Harsh | 3- Completed
S4 | S4 | US-018 | Google & GitHub OAuth Single-Click Authentication Integration | MUST HAVE | US-002 | Vamshi Krishna | 3- Completed
S4 | S4 | US-019 | Student Command Dashboard Layout Reconfiguration with KPI Cards | MUST HAVE | US-003 | Muthumenen M | 3- Completed
S4 | S4 | US-020 | Automated System Unit Testing & Case Verification | MUST HAVE | US-017 | Lohith Raj | 3- Completed
S4 | S4 | US-021 | Faculty Monitoring Dashboard & Interactive Guidance Feedback Modal | MUST HAVE | US-016 | Harshitha H S | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Lead Multi-Agent Architecture & System Data Flow Design | 2026-06-29 | 2026-07-10 | Harshitha H S (MAJOR ROLE) | Architecture | 3- Completed | 12
US-002 | 2 | Design MySQL ai_project_mentor schema & users table | 2026-06-29 | 2026-07-03 | Vamshi Krishna | Database | 3- Completed | 8
US-003 | 3 | Develop Student Registration & Profile Onboarding Interface | 2026-06-30 | 2026-07-06 | Muthumenen M | Design/UI | 3- Completed | 6
US-004 | 4 | Build Competency Skill Assessment Matrix UI & Scoring Logic | 2026-07-02 | 2026-07-08 | Lohith Raj | Design/UI | 3- Completed | 6
US-005 | 5 | Develop Project Submission Page & Pre-Loaded Academic Templates | 2026-07-06 | 2026-07-10 | Harsh | Coding | 3- Completed | 6
US-006 | 1900-01-05 | Develop Feasibility Analysis Agent & Scope Definition Agent Engines | 2026-07-13 | 2026-07-17 | Harshitha H S (MAJOR ROLE) | Coding/AI | 3- Completed | 12
US-007 | 1900-01-06 | Develop Tech Stack Agent & Milestone Planning Agent Engine | 2026-07-17 | 2026-07-24 | Harshitha H S (MAJOR ROLE) | Coding/AI | 3- Completed | 10
US-008 | 1900-01-07 | Develop Express REST API Endpoints (/api/projects/agent/unified) | 2026-07-13 | 2026-07-24 | Vamshi Krishna | Backend API | 3- Completed | 8
US-009 | 1900-01-08 | Build Multi-Agent Control Hub UI & Pipeline Action Trigger Cards | 2026-07-15 | 2026-07-21 | Muthumenen M | Design/UI | 3- Completed | 6
US-010 | 1900-01-09 | Implement Real-Time Execution Log Terminal Window | 2026-07-17 | 2026-07-23 | Lohith Raj | Coding | 3- Completed | 6
US-011 | 1900-01-10 | Build Active Project Summary Display Header & Storage Payload | 2026-07-20 | 2026-07-24 | Harsh | Coding | 3- Completed | 6
US-012 | 1900-01-11 | Build Dynamic Weekly Check-in Progress Engine & Status Badge Shifter | 2026-07-27 | 2026-08-04 | Harshitha H S (MAJOR ROLE) | Coding/AI | 3- Completed | 10
US-013 | 1900-01-12 | Implement Backend Chat Endpoints & Project Context Storage | 2026-07-27 | 2026-08-04 | Vamshi Krishna | Backend API | 3- Completed | 8
US-014 | 1900-01-13 | Build Nova AI Mentor Chat UI & Quick Action Prompt Chips | 2026-07-29 | 2026-08-06 | Muthumenen M | Design/UI | 3- Completed | 6
US-015 | 1900-01-14 | Develop Risk Assessment Agent & Plan-B Mitigation Fallback Engines | 2026-07-27 | 2026-07-31 | Lohith Raj | Coding/AI | 3- Completed | 8
US-016 | 1900-01-15 | Develop On-Demand Document Exporter (Synopsis, Methodologies, Slides PDF) | 2026-08-03 | 2026-08-07 | Harsh | Coding | 3- Completed | 8
US-017 | 1900-01-16 | Lead System Integration, Prompt Optimization & Final Presentation Prep | 2026-08-10 | 2026-08-20 | Harshitha H S (MAJOR ROLE) | Architecture | 3- Completed | 10
US-018 | 1900-01-17 | Implement Google & GitHub OAuth Single-Click Authentication Sync | 2026-08-12 | 2026-08-19 | Vamshi Krishna | Backend/Auth | 3- Completed | 6
US-019 | 1900-01-18 | Reconfigure Student Command Dashboard with KPI Cards & Launcher Grid | 2026-08-10 | 2026-08-14 | Muthumenen M | Design/UI | 3- Completed | 6
US-020 | 1900-01-19 | Conduct End-to-End System Testing & Unit Test Case Verification | 2026-08-14 | 2026-08-20 | Lohith Raj | Testing | 3- Completed | 6
US-021 | 1900-01-20 | Develop Faculty Monitoring Dashboard & Interactive Teacher Feedback Modal | 2026-08-11 | 2026-08-18 | Harsh | Design/UI | 3- Completed | 8

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 (M1) | 2026-07-02 | Impediments: Need DB schema for profiles. Action: Vamshi created MySQL tables; Harshitha H S reviewed data models.
Sprint 1 (M1) | 2026-07-07 | Impediments: Template cards click handling. Action: Muthumenen M & Harsh updated submit-project.js handlers.
Sprint 2 (M2) | 2026-07-16 | Impediments: Gemini API rate limits. Action: Harshitha H S implemented rich offline fallback generators in aiAgents.js.
Sprint 2 (M2) | 2026-07-21 | Impediments: Execution log window formatting. Action: Lohith Raj & Vamshi synced terminal stream logs.
Sprint 3 (M3) | 2026-07-30 | Impediments: Inference latency >1.5s. Action: Lohith Raj & Harshitha H S deployed lightweight local classifiers (<500ms).
Sprint 3 (M3) | 2026-08-04 | Impediments: Document export layout in PDF. Action: Harsh & Muthumenen M formatted print CSS styling.
Sprint 4 (M4) | 2026-08-13 | Impediments: Student dashboard empty white space. Action: Muthumenen M & Harshitha H S reconfigured dashboard layout.
Sprint 4 (M4) | 2026-08-18 | Impediments: Teachers needed direct feedback feature. Action: Harsh & Harshitha H S built Faculty Feedback Modal System.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 (M1) | 2026-06-29 | 2026-07-10 | Harshitha H S (MAJOR) | Leading Multi-Agent system architecture design | Monolithic prompts | Daily architecture sync | Defined agent schemas.
2 | Sprint 1 (M1) | 2026-06-29 | 2026-07-10 | Vamshi Krishna (Minor) | Designing MySQL users and projects database tables | Manual DB queries | Schema optimization | Created MySQL db script.
3 | Sprint 1 (M1) | 2026-06-29 | 2026-07-10 | Muthumenen M (Minor) | Building student registration onboarding page | Static forms | UI responsiveness | Completed onboarding UI.
4 | Sprint 1 (M1) | 2026-06-29 | 2026-07-10 | Lohith Raj (Minor) | Developing skill assessment matrix & scoring logic | Hardcoded scores | Component styling | Built skill matrix.
5 | Sprint 1 (M1) | 2026-06-29 | 2026-07-10 | Harsh (Minor) | Creating project submission page & template cards | Plain text area | Card click handlers | Built submission UI.
6 | Sprint 2 (M2) | 2026-07-13 | 2026-07-24 | Harshitha H S (MAJOR) | Building Feasibility, Scope, Stack & Timeline Agents | Single prompt logic | Agent decoupling | Delivered 4 core AI agents.
7 | Sprint 2 (M2) | 2026-07-13 | 2026-07-24 | Vamshi Krishna (Minor) | Developing Express REST API endpoints | Sync handlers | Async routing | Created agent REST routes.
8 | Sprint 2 (M2) | 2026-07-13 | 2026-07-24 | Muthumenen M (Minor) | Building Multi-Agent Control Hub card grid | Generic buttons | Card hover effects | Completed Agent Hub UI.
9 | Sprint 2 (M2) | 2026-07-13 | 2026-07-24 | Lohith Raj (Minor) | Implementing live execution log terminal window | Unformatted logs | Terminal styling | Built execution log window.
10 | Sprint 2 (M2) | 2026-07-13 | 2026-07-24 | Harsh (Minor) | Building active project summary display header | Empty headers | State persistence | Completed summary header.
11 | Sprint 3 (M3) | 2026-07-27 | 2026-08-07 | Harshitha H S (MAJOR) | Building dynamic weekly check-in progress engine | Static badges | Live status updates | Created dynamic status shifter.
12 | Sprint 3 (M3) | 2026-07-27 | 2026-08-07 | Vamshi Krishna (Minor) | Implementing backend chat endpoints for mentor | Unsaved chat | Context passing | Built chat API endpoints.
13 | Sprint 3 (M3) | 2026-07-27 | 2026-08-07 | Muthumenen M (Minor) | Building Nova AI Mentor chat desk & prompt chips | Plain chat box | Quick prompt chips | Completed Nova AI Chat UI.
14 | Sprint 3 (M3) | 2026-07-27 | 2026-08-07 | Lohith Raj (Minor) | Developing Risk Assessment Agent & Plan-B fallbacks | Ignoring latency | Local classifiers | Delivered Risk Agent.
15 | Sprint 3 (M3) | 2026-07-27 | 2026-08-07 | Harsh (Minor) | Developing On-Demand Document Exporter & PDF generator | Plain text export | Formatted reports | Built Document Exporter.
16 | Sprint 4 (M4) | 2026-08-10 | 2026-08-20 | Harshitha H S (MAJOR) | Leading end-to-end integration & defense prep | Unreviewed code | System validation | Completed presentation deck.
17 | Sprint 4 (M4) | 2026-08-10 | 2026-08-20 | Vamshi Krishna (Minor) | Integrating Google & GitHub OAuth single-click login | Manual login | OAuth profile sync | Completed OAuth auth.
18 | Sprint 4 (M4) | 2026-08-10 | 2026-08-20 | Muthumenen M (Minor) | Reconfiguring student command dashboard layout | Wasted white space | Compact KPI cards | Completed dashboard UI.
19 | Sprint 4 (M4) | 2026-08-10 | 2026-08-20 | Lohith Raj (Minor) | Executing unit test cases across all modules | Untested routes | Automated testing | Verified 7 test cases PASS.
20 | Sprint 4 (M4) | 2026-08-10 | 2026-08-20 | Harsh (Minor) | Developing Faculty Monitoring Dashboard & Feedback Modal | Static cards | Interactive modal | Built Faculty Guidance Modal.