## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Muthumenen M | 2026-07-06 | Pre-loaded template cards not populating submission text area upon click | Sprint 1 | Muthumenen M | User Interface | Added active-template class toggle and focus listener in submit-project.js | 2026-07-07 | Closed | Verified fix across all 4 template cards.
2 | Harshitha H S | 2026-07-16 | API rate limit error during multi-agent blueprint generation | Sprint 2 | Harshitha H S | Logical | Implemented rich offline fallback generators in aiAgents.js for all 5 agents | 2026-07-17 | Closed | Tested offline fallback report generation.
3 | Lohith Raj | 2026-07-30 | High model inference latency (>1.5s) during real-time sentiment analysis | Sprint 3 | Lohith Raj | Performance | Switched heavy API calls to lightweight distilled local classifiers (<500ms) | 2026-07-31 | Closed | Latency benchmark reduced to 420ms.
4 | Harshitha H S | 2026-08-04 | Milestone status badges showing 100% completed for newly submitted projects | Sprint 3 | Harshitha H S | Logical | Added completedCheckinWeek localStorage tracking (0% initial pending state) | 2026-08-05 | Closed | Newly submitted projects now start at 0%.
5 | Harsh | 2026-08-12 | Excessive empty white space on student command dashboard layout | Sprint 4 | Harshitha H S | User Interface | Reconfigured dashboard.html with 4 compact KPI cards & quick action launcher grid | 2026-08-13 | Closed | Verified clean, responsive layout.
6 | Vamshi Krishna | 2026-08-14 | Faculty advisors unable to send guidance feedback when student teams get stuck | Sprint 4 | Harsh | Logical | Built Interactive Faculty Feedback Modal & live student banner notification system | 2026-08-15 | Closed | Faculty guidance note displays live on student dashboard.
7 | Harshitha H S | 2026-08-17 | Social login buttons not creating authenticated user context | Sprint 4 | Vamshi Krishna | Standards | Integrated handleSocialAuth handler for Google & GitHub OAuth single-click login | 2026-08-18 | Closed | Verified user context saved to localStorage.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others